## Slide 1
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 0
Establish Accreditation Response Committee
Self Study Report Committee
Celebration/ Recognition
QEP Proposal
Self Study Report
QEP Implementation Committee
On –site Visit
Establish Processes for Future Compliance Committee
Celebration/ Recognition

## Slide 2
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 1
Accreditation Response Committee
QEP Implementation Committee
QEP Implementation
Establish 10 yr. Professional Accreditation Cycle
Establish 10 yr. Program Assessment Cycle
QEP Status Report
Recommendation Report
Evaluate Data Gathering Strategy
Recommend Strategy
Establish Processes for Future Compliance
Data Gathering Confirmation Dissemiation
Establish Training Needs

## Slide 3
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 2
QEP Implementation Committee
QEP Implementation
QEP Status Report
Processes for Future Compliance Implementation/Revision
Implement Training Curriculum

## Slide 4
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 3
QEP Implementation Committee
QEP Implementation
QEP Status Report
Implement Training Curriculum

## Slide 5
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 4
QEP Implementation Committee
QEP Implementation
QEP Status Report
5th Year Readiness Committee
Selection of Reporting Strategy
Action Plan for Fifth Year Compliance
Implement Training Priorities
Population of Report

## Slide 6
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 5
QEP Implementation Report
5th Year Compliance Implementation
QEP Status Report
QEP Implementation Committee

## Slide 7
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 6
Celebration
QEP Transition to Institutional Effectiveness
5th Year Report
5th Year Report Committee
Training Priorities
5th Year Follow-up
Celebration/ Recognition

## Slide 8
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 7
SACS Readiness Committee
Confirm Compliance Tracking Strategy
SACS Readiness Report
5th Year Follow-up
Celebration/ Recognition

## Slide 9
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 8
Establish QEP Planning Committee
SACS Readiness Committee
SACS Readiness Report
Implementation for Compliance
QEP Data Requirements Identified
Implement Training Priorities

## Slide 10
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 9
QEP Planning Committee
Select Reporting Strategy
QEP Pilot
Population of Report
SACS Readiness Committee
SACS Report Committee
Implementation for Compliance
SACS Readiness Report
QEP Data Gathering and Selection
Implement Training Priorities

## Slide 11
QEP Plan
June
July
August
September
October
November
December
January
February
March
April
May
June
Year 10
QEP Planning Committee
Preparation for On-Site
Establish Response Committee
Self Study Report Committee
Celebration/ Recognition
Self Study Report
QEP Implementation Committee
On –site Visit
Celebration/ Recognition
Processes for Future Compliance Committee
Implementation for Compliance

## Slide 12
Training
June
July
August
September
October
November
December
January
February
March
April
May
June
Ongoing Infrastructure Maintenance
Implementation Review
Action Plan Implementation Previous Cycles
Assessment Plan
Assessment Plan Implementation
Assessment Analysis
Action Plan Implementation from Previous Cycles
Institutional Effectiveness
Objectives Revision
Performance Objective Implementation
General Education Assessment Plan
Monitor Data Gathering
Implementation Review
Implementation Review
Action Plan Implementation Previous Cycles
Annual Report

## Slide 13
Year 0
Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Year 7
Year 8
Year 9
Year 10
Year 0
Periods of Compliance without Infrastructure Maintenance
Compliant
Compliant
Benefit to Institution
Infrastructure Level
Compliant
Non-Compliant

## Slide 14
Year 0
Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Year 7
Year 8
Year 9
Year 10
Year 0
Impact of Non-Compliance
Non Compliant
Cost
Cost
Benefit to Institution
Compliant
Non-Compliant

## Slide 15
Chart: Cumumulative Cost Vs. Benefit Without Infrastructure Maintenance
| Year 1 | Year 2 | Year 4 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20
Benefit | -1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10
0
+
-

## Slide 16
Chart: Cummulative Cost Vs. Benefit With Infrastructure Maintenance
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
Cost | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
Benefit | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
0
+

## Slide 17
Impact of On-Going Compliance
Compliant
Benefit to Institution
Non-Compliant
Infrastructure Level
Year 0
Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Year 7
Year 8
Year 9
Year 10
Year 0
Maintenance Cost

## Slide 18: Infrastructure
Examples of Infrastructure
  Existing Processes
  Accountability Processes
  Existing Alignment
  Existing Faculty
  Leadership
  Technology
  Faculty Credentials Database
  Leadership
  History
  Resources
  Traditions
Threats and Opportunities
  Lack of planning
  Failure to monitor
  Lack of Accountability
  Lack of rewards and recognition
  Lack of implementation
  New Personnel
    New Leadership
    New Faculty
  Lack of ongoing training
  Budget
  Unfunded mandates
  Institutional Change
  Experience
  Loss of institutional capacity
  Increased expectations
  Inability to articulate needs
  Loss of human capital