## Slide 1: LMS update
Jeff Delaney, Ed.D. Associate Vice Chancellor Information Technology Services

## Slide 2
IG1 – Aug 2012
Augusta State College
Bainbridge College
College of Coastal Georgia
East Georgia College
Middle Georgia College
IG2 – Jan 2013 | 
Abraham Baldwin Agricultural College | Georgia ONmyLINE
Albany State University | Georgia Perimeter College
Armstrong Atlantic State University | Georgia Southwestern State University
Atlanta Metropolitan College | Georgia State University
Clayton State University | Gordon College
Columbus State University | Kennesaw State University
Dalton State College | Macon State College
Darton College | North Georgia College and State University
Fort Valley State University | Savannah State University
Gainesville State College | Skidaway Institute of Oceanography
Georgia College and State University | South Georgia College
Georgia Gwinnett College | Southern Polytechnic State University
Georgia Highlands College | University of West Georgia
 | Waycross College
IG3 – May 2013
Georgia Health Sciences University
University of Georgia
Valdosta State University

## Slide 3: Status Report
Status | Project Milestones and Tasks | % Complete | Completion Date*
Complete | Project Core Team Kickoff : draft charter, org chart, initial communication plan, roles & responsibilities, change management plan | 100% | 10/13/11
Complete | Campus Meetings | 100% | 11/16/11
Complete | Implementation Groups Communicated | 100% | 1/12/12
Complete | Project Milestone Plan Communicated – High Level | 100% | 1/18/12
Complete | Architecture Design Complete | 100% | 1/20/12
Complete | Hardware Ordered for IG1 & IG2 (non-unique) | 100% | 1/27/12
Complete | IG1 Kickoff Meeting | 100% | 1/27/12
Complete | Onsite D2L Consulting | 100% | 1/27/12
Complete | Faculty Training Environment Complete for IG1 | 100% | 1/31/12
Complete | Hardware Received | 100% | 2/16/12
Complete | D2L Install / Org Setup Complete (qdev) | 100% | 2/24/12
Complete | Admin & Faculty Train-the-Trainer for IG1 | 100% | 2/24/12
Complete | Storage Upgrade Complete | 100% | 3/12/12
Complete | D2L Install / Org Setup / Refresh Complete (fdev2) – New Confirmed Date with D2L | 100% | 3/13/12

## Slide 4: Status Report
Status | Project Milestones and Tasks | % Complete | Completion Date*
Not Started | Conduct IG2 Kickoff |  | 4/04/12
At Risk | Ga Southern Content Migration – Phase I | 5% | 4/13/12
At Risk | GaMod Development & Testing Complete |  | 4/20/12
Not Started | Install #3 (xprod) |  | 4/26/12
At Risk | Pre-Production Environment Released to IG1 Institutions |  | 5/10/12
At Risk | Beta Testing Complete (SIS batch) |  | 5/25/12
At Risk | Content Migration – IG1 Phase I Complete |  | 5/30/12
Not Started | Install #4 (qprod) cluster at UGA |  | 5/31/12
At Risk | Pre-Production Environment Released to IG2 Institutions |  | 6/10/12
Not Started | Install #5 (xtest) |  | 6/11/12
Not Started | Install #6 (qtest) |  | 7/16/12
Not Started | Install #7 (xdev) |  | 7/16/12
At Risk | Implementation Group 1 – Live/Teaching |  | 08/2012
At Risk | Implementation Group 2 – Live/Teaching |  | 01/2013
At Risk | Implementation Group 3 – Live/Teaching |  | 05/2013

## Slide 5: Data Warehouse (ADM) Update

## Slide 6: Status Report
Status | Milestones | % Comp | Start Date* | Completion Date*
Complete | Campus Kick Off Meeting | 100% | (A) 11/11/11 | (A) 11/11/11
Complete | Final ETL Requirements released to Campuses | 100% | (A) 11/11/11 | (A) 12/23/11
Complete | Campus Data Submission Training | 100% | (A) 03/01/12 | (A) 03/22/12
Complete | USG ODS available for early data loading | 100% | (A) 01/04/12 | (A) 03/01/12
On-Time | Campus submit data into new data warehouse | 17% | (A) 03/01/12 | (P) 04/24/12
On-Time | Campus Data Submission Assistance Period | 0% | (P) 04/24/12 | (P) 05/07/12
On-Time | Parallel Testing of new system and current ADM begins | 0% | (P) Aug 2012 | TBD
On-Time | Second Prototype USO Reporting System | 0% | (A) Mar 2012 | (P) 05/02/12
On-Time | Strategic Planning for Information Access | 0% | (P) Apr 2012 | (P) 07/03/12

## Slide 7: Status Report
Status | Milestones | % Comp | Start Date* | Completion Date*
On-Time | Current ADM History Load | 0% | (P) May 2012 | (P) 07/15/12
On-Time | BI Tool Set (Cognos) Training for USO | 0% | (P) July 2012 | (P) 07/15/12
On-Time | First Iteration Enterprise Data Warehouse available for reporting | 0% | (P) May 2012 | (P) 8/1/12
On-Time | BI Tool Set (Cognos) Training for Campuses | 0% | (P) Aug 2012 | (P) 09/16/12
On-Time | First SIRS History Load | 0% | (P) July 2012 | (P) 08/26/12
On-Time | Third Prototype USO Reporting System | 0% | (P) July 2012 | (P) 09/15/12
On-Time | Final History Load | 0% | (P) Aug 2012 | (P) 10/15/12
On-Time | Retire OLD ADM | 0% | (P) May 2012 | (P) 03/15/13

## Slide 8: Questions?